Green management In schools For Sustainability

GIFs

2022-1-RO01-KA220-SCH-000088088

Project Implementation Plan

| No. | Objectives | Work Packages | Necessary resources (human, financial) | Responsible | Period | Expected results/outcomes | Indicators |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Partnership development at consortium level Ensuring quality project management | WP 1 | The project team of each partner organization 24000 euros | CNSH Tecuci, Romania | 01/09.2022 - 31.08.2024 | Increasing cooperation on green building practices | The quality of the project’s results The quality of the dissemination Quality evaluation from external stakeholders |
| 2 | Increase participating organisations’ knowledge regarding green building practices through a research phase; Create an educational material to raise awareness and increase the knowledge of teachers and schools’ staff members regarding green building practices. Providing teachers and schools’ staff members with knowledge regarding green building practices and methodologies on how to implement them in their schools. Promote schools’ cooperation on green building practices | WP 2 | 1 researcher per partner organization to develop the modules assigned. 1 stakeholder per partner organization with the profile of expert in green building practices 1 researcher per partner organization involved to improve the Guide’s content based on the reviews and based on the WP’s coordinator instructions. Each school involved in the process (participating organization and associated organisation) will select one representative among their schools’ staff member in order to organize the implementation of the green building practices. Students and teachers of each partner organization, for implementation of the green building practices. 28700 euros | Nachalno uchilishte Tsani Ginchev, Bulgaria | 01.09.2022 – 30.06.2023 | 1 Guide explaining the general concept of green building practices and such practices can be implemented in schools with concrete examples of existing practices already implemented in European schools; The concrete implementation of green building practices in the participating schools. | Concrete participation of all participating organisations within the research phase and the development of the Guide The Guide will be reviewed by real experts in each one of the partner countries to ensure the quality of the content Number of downloads of the guide after one year of the project’s completion: 50 Number of likes and shares to the posts disseminating the Guide on the social media at the end of the project: 200 Number of practices contained in the guide implemented concretely in the participating school organisations: at least 3 practices per school partner Number of experts taking part in the reviewing process: 5 (1 per partner organisation) |
| 3 | Promote cooperation between schools and NGOs working with Non-Formal Education with young people to propose innovative ways of teaching at school; Offer a way to include the topic of Green Building Practices into school education to reach a wider impact; Create a material addressed to schools’ staff members which contains activities including NFE activities to be implemented with their students. Provide teachers and schools’ staff members with methodologies on how to raise students awareness on green building practices and involve them in the process of implementing them at schools | WP 3 | Co-creation sessions The participants will be as follows: - At least 1 representative for each school partner with the profile of teacher; - At least 2 representatives of MVNGO (1 trainer and 1 project manager). Joint Staff Training Event Participants: No. 5 participants per partner belonging to the categories of youth workers, school staff, teachers. Local activities - 10 participants per school partner; - Aged between 9 and 13 years old; - Registered as student in the school partner at the moment of the local activities; - Students with disabilities will have priority in the selection process. 30100 euros | Mine Vaganti NGO, Italy | 01.06.2023 – 31.01.2024 | The main WP’s result will be a Toolkit containing Non-Formal Education activities to involve the students in the process of implementation of green building practices. The Toolkit will also contain a guideline to help Schools to implement these activities. | Participants into the co-creation session of the Toolkit The Toolkit will be tested and evaluated through local activities in each one of the partner countries. Number of participants to the local activities resulting from the Toolkit implemented by each partner school: 10 Number of downloads of the Toolkit after one year of the project’s completion: 50 Number of likes and shares to the posts disseminating the Toolkit on the social media at the end of the project: 200 Number of the schools among those involved in the present project which will have used the Toolkit after one year completion of the project (survey): at least 3 |
| 4 | Create a Council designed to promote the cooperation among European schools to implement green building practices; Sharing of new green building practices; Promote new initiatives in green building management | WP 4 | Establishment of the GIFs ESGC All partners, under the coordination of the WP leader, will produce the results of this activity where the 2 project managers of each partner organization will be involved. The Council will count 2 representatives per school member of the Council with the following profile: - Teacher or school staff member with educational experience; - Experience in education sector of at least 2 years. First Summit of the GIFs ESGC 2 representatives per school member of the Council will take part in the Summit. They will have the following profile: - Teacher or school staff member with educational experience; - Experience in education sector of at least 2 years. Social Campaign Participants: All the schools’ staff members, teachers and students will be actively involved in the social campaign. 19200 euros | Özel Filiz Anadolu Lisesi, Türkiye | 01.12.2023 – 01.08.2024 | Creation of a European School Green Council; The first Summit of the ESGC. | Implemented of another Summit after the project’s completion Success in the implementation of green building practices Number of participants to the first Summit: 20 Number of new initiatives implemented in terms of green building practices one year after the project’s completion: 10 Number of schools being part of the council one year after the project’s completion: 20 Participation to the Social Campaign: at least 100 posts contributing to the social campaign one year after the project’s completion (by sharing green building practices at school with the selected Hashtag). |
| 5 | Ensure the project’s visibility and the one of its results and impacts; Ensure the sustainability of the project’s results; Establish follow-up activities. | WP 5 | Audience: - General public; - Schools; - Other institutions bodies active in the educational field; - Any entity active in the green sector; - Stakeholders; - Members of the press; - Universities; - Policy-makers at local, regional and national levels; - Participants of the local phases. 18000 euros | Mine Vaganti NGO, Italy | 01.09.2022 – 31.08.2024 | Project’s visibility at the local, regional, national and European level; Project’ website where all the materials produced will be uploaded and accessible to the large public; Create a basis for future project ideas and actions to insure the project's long-term existence and impact. | Focus groups with stakeholders will be organized in each partner country to assess stakeholder institutions' adoption of project practices. Total social media posts and shares: at least 60 posts and 600 social media shares and likes are expected by the end of the project. Participation in Dissemination Conferences: Each partner country must have at least 30 participants to the National Dissemination Conference |

Working plans

| Work packages | Activities |
| --- | --- |
| WP 1 | During the Kick-off meeting, the Coordinator will present to the partners the Partnership Agreement which will contain the roles and responsibilities of each partner. It will contain also a GANTT of project implementation with all related deadlines. Each partner will sign the document during the Kick-off meeting as a proof of commitment. The Management Plan will be drafted at the beginning of the project by the Project’s coordinator and introduced during the Kick-Off meeting to all partners. The Management Plan will contain all the details regarding the tasks and sub-tasks of all partners together with the dedicated deadlines. In order to monitor the work of each partner organization, the Quality and Evaluation Committee together with the Management Committee will make a control of the project’s implementation on a 3 month-basis through the Progress Reports. They will also control the documents and products mentioned in the Reports that will be uploaded in the shared Google folder. The Quality and Evaluation Committee will produce a Quality Report where the work of each partner organization will be reported, and the report will be submitted to the project’s coordinator. The proejct’s coordinator will also monitor the ongoing work through Trello. In case of the deadlines would not be meet or in case of poor quality of task performance, project’s coordinator will be able to intervene and solve the issue. A Procurement Plan will be presented by the project’s coordinator to the Kick-Off meeting where all the budget details will be defined for each task. Accordingly, quarterly financial reports will have to be produced by all the partners reporting the details of all expenses done within the project’s implementation within the reporting period as well as of its function for the performance of project tasks/activities. The project’s coordinator will be in charge of monitoring the use of budget at the level of the partner organization, as well as providing early warning in case of expenses exceeding expected standards of quality and allocations. A Risk Management Plan will be established at the beginning of the project by the project’s coordinator that will present the document during the Kick-Offf Meeting in order to discuss it with the partners, possibly complete it and collect the agreement of all partners on the last version of the document. Risk Management will be conducted by the project’s coordinator, with the support of the Risk Management Committee, and will apply the Risk Management Plan. In case a situation not provided in the Plan would occur, the project’s coordinator, together with the Risk Management Committee, will take the necessary and adapted decision. Potential risks and relative corrective measures: Risk 1: Misunderstandings or conflicts within the Consortium Correction: Constant online communication within the Consortium (Zoom, Trello, Dropbox, Email), Production of Minutes of physical and virtual meetings; Appointment of a Conflict Resolution Committee (1 representative per partner) in case of conflict among partners. Risk 2: Problems with the delivery of expected results Correction: The coordinator will provide support to partner organizations by means of real-time communication (Skype, Email, Social Media, and Phone, etc.). It will be able to address directly and consult the National Agency about any cases of doubts and difficulties emerging during the process of implementation. Risk 3: Problems in respecting deadlines Correction: Constant Monitoring and Intermediate Evaluation will provide all partners with an overview of each partner's progress. Overview and early warning about incoming deadlines will be provided through the Gantt Project software. Constant communication, regular virtual meetings, and Transnational Partners' Meetings will provide a framework for applying modifications to the work programme and/or arrangements of support that might be needed. |
| WP 2 | The WP will contain the following activities: - Research phase (1) - Guide’s development (2) - Guide’s review (3) - Local activity: implementation of green building practices in schools (4) The division of tasks and responsibilities of the WP will be as follows: 1: under the lead of Nachalno Tsani Ginchen, all the partners will execute a research phase (desk research) at the national and at the European level. 2: under the lead of Nachalno Tsani Ginchen, all the partners will contribute to the development of the Guide. This Guide will contain the following elements: - What is a Green Building and why it is important to respond environmental issues, what are its positive impacts on the planet; - How to turn a building into a green building, with examples of existing green building practices already in place; - A step-by-step guideline to set up green building practices; - A template Environmental Action Plan; - Templates to be used to assess progress and results. The structure of the Guide will be discussed among the partners based on the research phase accomplished by all partners. The final decision will belong to the WP’s coordinator. The partners will select through a vote a set of practices found during the research phase and will elaborate a guideline on how to proceed with their implementation in schools. 3: All partners will be in charge to submit the first draft of the Guide to a national expert in the field of green building practices. An evaluation grid will be provided to these experts for them to provide proper feedback on the quality of the material. 4: The selected practices will be implemented in the school partners or associated partners following the guidelines elaborated in the previous phase through local activities. |
| WP 3 | Co-creation sessions The co-creation sessions will by itself create a cooperation among schools and NGOs working with NFE and will serve as a way to promote such cooperation in the future in case of success. The co-creation phase is fundamental to the creation of the Toolkit to be implemented with the students as it will contribute to increase the quality of the material by ensuring a cross-sectorial approach. The purpose of involving both schools and NGOs working with NFE is to offer innovative material in order to encourage knowledge and skills transfer to the students regarding green building practices. The participants will be as follows: - At least 1 representative for each school partner with the profile of teacher; - At least 2 representatives of MVNGO (1 trainer and 1 project manager). Joint Staff Training Event The training will be carried out by a trainer of MVNGO to support teachers and other schools’ staff members to be familiar with NFE methodology and to use it as a tool to involve their students into the process of implementation of green building practices at school. This activity will consequently promote the cooperation among NGOs working with NFE and schools. Also, in order for the teachers and schools’ staff members to implement the activities of the Toolkit, it is fundamental for them to attend a propre training on how to implement such kind of activities with their students in order to include it into school education. Participants: No. 5 participants per partner belonging to the categories of youth workers, school staff, teachers. Local activities The local activities will allow the partners to get a proper evaluation of the Toolkit and ensure this way the quality of the material. - 10 participants per school partner; - Aged between 9 and 13 years old; - Registered as student in the school partner at the moment of the local activities; - Students with disabilities will have priority in the selection process. The selection process will be done through direct communication to the children and indirect communication to the students’parents. The written authorization of the participants’ parents or legal representative will be required. |
| WP 4 | Establishment of the GIFs ESGC The partners, under the lead of the WP’s coordinator, will establish the GIFs European Schools Green Council by appointing the first two representatives per school. The partners will produce a Commitment Agreement which will be signed by all schools’ members the Council and by all the new schools which may integrate the Council in the future. As a first step, the council will produce a Green Building Management Strategic Plan where the members of the council will write the date, the place and the agenda of the next Council Summit, the objectives of the council, the strategy they want to carry out in order to achieve the objectives. The Council will be designed to meet every year. First Summit of the GIFs ESGC The partners will organize the first Summit of the ESGC where the members will produce their first Report regarding the green building practices they implemented and the activities they used in order to involve their students. The members will also discuss new green building initiatives to implement in the following year and set the date of the next Summit. A template of Report will be produced by the consortium to provide the schools with the necessary guidance. Social Campaign The Social Campaign activity will be led by MVNGO. The partnership will agree on a hashtag to use for the social campaign (e.g. #GreenYourSchool). Teachers, schools’ staff members, with the involvement of their students, will work on the social campaign by posting on Instagram short videos/pictures of what is done in the school to become Green Buildings and by using the selected hashtag. The partners will produce a Communication Plan for the Social Campaign. The first draft will be made and proposed to the partners by MVNGO. Teachers and schools’ staff members will implement the communication plan that has been prepared by the Consortium. |
| WP 5 | Dissemination Activities: A.1 Communication, dissemination and exploitation activities. The Applicant and Dissemination Coordinator will realise the following preparatory activities whose outputs will be scheduled in the plan for dissemination and exploitation of results: - Creation of the project logo and use of the Erasmus + logo in all the project materials; - Creation of the social media accounts of the project and the website of the project; A.2 Digital communication - Communication through digital means will last for the entire duration of the project. - Communication of project activities through the social media; - Monthly newsletter of the project; - Communication carried out by partner organisations through their own websites and social media. - Results and outputs will be shared through the social media accounts and the newsletter; A.3 Communication and dissemination through physical means. - Publishing a press release at the moment of transnational project meetings, the start and the end of the learning activities, the local multiplier events and communication to local - Interviews with local stakeholders and collection of feedback about project results and learning activities; A.4 The Conference will be implemented at the national level, as an open event, with an audience set to amount to 35 individuals. Audience: - General public; - Schools; - Other institutions bodies active in the educational field; - Any entity active in the green sector; - Stakeholders; - Members of the press; - Universities; - Policy-makers at local, regional and national levels; - Participants of the local phases. The agenda of the Conference will be the following: - Introduction to the project; - Activities and results achieved; - Presentation of participants' testimonials of the local phases; - Presentation of the Intellectual outputs; - Official Closing; - Evaluation and co-design of follow-up and new partnership. |